## W & G
JIGAWA STATE DUE PROCESS AND PROJECT MONITORING BUREAU
PROCUREMENT PLAN TEMPLATE
| PROCUREMENT PLAN FOR WORKS AND GOODS CONTRACTS |  |  |  | Construction of Zonal office Hadejia
| MINISTRY/ AGENCY: | Local Government Audit
| BUDGET YEAR: | 2021
| PROJECT PARTICULARS |  |  |  | BASIC DATA |  |  | PROJECT PREPARATION |  |  |  | BIDDING PERIOD |  | BID EVALUATION & AWARD |  |  | CONTRACT MANAGEMENT & ADMINISTRATION |  |  |  | ANY OTHER REMARKS
| Project Description | Economic Code | Package No./File No. | Lot No. | Approved Threshold/ Budgeted Amount (Naira) | Estimated Amount in Naira | Procurement Method | Preparation & Submission of documents by MDAs | Post Review/ Vetting | Advert for Pre - Qualification | Pre-Qualification | Bid Invitation | Bid receipt and opening | Bid Evaluation& Report | Consideration of TEC Recommendation | Due Process Certificate of No Objection | Contract Approval & Offer | Contract Signing | Delivery/handover and acceptance | Final Payment
Date: Plan | Construction of Zonal Office building phase I Hadejia Zone | 01400002001000 100006 | N.A | N.A | N20,million | 20 million | selective | 25/01/2021 | 2021-10-02 | N.A | N.A | N.A | N.A | N.A | N.A | N.A | 19/02/2021 | 26//02/2021 | 30/04/2021 | 14/05/2021 | We considerred limited period as result of rapid high cost of building material. However, provision wiill be made to in case of variation.
Date: Actual
Cost :Plan
Cost: Actual
Responsibility

## CS
PROCUREMENT PLAN FOR CONSULTING SERVICES.
MINISTRY/ AGENCY:
BUDGET YEAR:
Project Description | Package Number | CONTRACT TYPE |  |  |  | PREPARATION OF PROPOSALS |  |  |  | SHORTLIST |  | CONSULTANT PROPOSAL |  | PROPOSAL EVALUATION AND NEGOTIATION | [5 empty] | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
|  | Lumpsum or Time-Based | Budgetary Amount in Naira | Plan Vs Actual | Approval Threshhold | Preparation and Submission by MDAs | MDA Approval/ LASPPA 'Certificate of Compliance" | Advertisement | Lead-Time Beforte Shortlist | Submission Date | MDA Approval/ LASPPA 'Certificate of Compliance" | Invitation Date | Submission / Opening Date | Submission Evaluation Report (T) | MDA Approval/ LASPPA 'Certificate of Compliance" | Opening/ Evaluation of Financial Proposals | Submission Evaluation Report (T) (F) | Negotiation (if any) | Certificate of Clearance Date | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion